GoLocal → Indian Food Delivery Platform

Complete Product · Engineering · Business Roadmap

Transforming an existing Medusa v2.14.2 eCommerce platform into a
production-grade Indian food delivery ecosystem
(Swiggy / Zomato / Blinkit / Zepto / Uber Eats style)

| Prepared for | Platform | Stack | Date |
| --- | --- | --- | --- |
| BlackBull / GoLocal | Indian Market | Medusa v2 + Next.js 15 + React Native | May 2026 |

SECTION 1 — GAP ANALYSIS

A thorough audit of the existing GoLocal Medusa v2.14.2 platform against what is required to operate a production Indian food delivery service. This analysis drives all subsequent effort estimates.

1.1  What Already Exists & Is Production-Ready

| System / Feature | Status | Detail | Food Delivery Value |
| --- | --- | --- | --- |
| Medusa v2.14.2 Backend | ✅ Production | Node.js + TypeScript, port 9000 | Core API engine — do NOT replace |
| Product Catalog | ✅ Built | Products, variants, pricing (pence), images | → Restaurant menu items |
| Category Hierarchy | ✅ Built | Nested categories with handles | → Menu categories (Starters, Mains…) |
| Order System | ✅ Medusa Core | Cart → checkout → order lifecycle | → Food order lifecycle |
| Customer Auth | ✅ Built | JWT + cookie, account pages | → Extend with phone OTP |
| Staff Portal (RBAC) | ✅ 13 permission keys | Next.js /staff with 13+ pages | → Restaurant & ops portal |
| Custom Discounts Module | ✅ Production | product/category/global scope, scheduling | → Extend for food promos |
| Promotional Banners | ✅ Production | Live preview, scheduling, CTA | → App banners/offers |
| PostgreSQL + MikroORM | ✅ Production | Migrations, custom tables | → Main database |
| Coolify VPS Deployment | ✅ Live | Docker + webhook CI/CD | → Reuse infrastructure |
| Next.js 15 Storefront | ✅ Production | App Router, RSC, cache tags | → Web ordering interface |
| Shipping Options | ✅ Medusa Core | Standard + Express seeded | → Replace with delivery fee engine |
| Tax Regions | ✅ Medusa Core | 7 tax regions seeded | → Reconfigure for Indian GST |
| Price Lists | ✅ Medusa Core | Volume + customer-group pricing | → Time-based / surge pricing |
| Draft Orders | ⚡ Installed | @medusajs/draft-order installed, no UI | → Scheduled/pre-orders |
| Payment Gateway | ❌ NOT connected | Stripe SDK installed, zero config | → Must replace with Razorpay |
| Email Service | ❌ NOT connected | No provider integrated | → Add Resend + templates |
| Orders Staff Page | ❌ NOT built | Medusa admin /app has it | → Build in staff portal |
| Realtime / WebSockets | ❌ None | No Socket.io, no SSE, no Redis pub/sub | → Build from scratch |
| Push Notifications | ❌ None | No FCM / APNs configured | → Firebase integration needed |
| Mobile Apps | ❌ None | Web-only currently | → React Native / Expo build |
| Location / Maps | ❌ None | No Google Maps integration | → Core food delivery requirement |
| Rider System | ❌ None | No delivery partner concept | → Build entire rider subsystem |
| Multi-Vendor / Restaurant | ❌ None | Single-store currently | → Multi-vendor architecture needed |

1.2  Systems That MUST Be Built From Scratch

Multi-vendor restaurant management system (separate from Medusa admin)

Location & address system — Google Maps, saved addresses, delivery zones

Delivery fee calculation engine (base + per-km + surge + free threshold)

Real-time order tracking (WebSocket / SSE + Redis pub/sub)

Rider / delivery partner subsystem (onboarding, assignment, GPS, earnings)

Indian payment gateway — Razorpay (UPI, cards, wallets, COD, net banking)

OTP-based phone authentication (MSG91 / Twilio)

Firebase push notifications (FCM for Android, APNs for iOS)

Customer-facing mobile app (React Native + Expo)

Rider mobile app (React Native + Expo)

GST tax structure for India (5% restaurant food, 18% platform fee)

Rating & review system (order-verified reviews)

Cancellation & refund workflows with time-based policies

In-app wallet system with cashback and recharge

Loyalty / rewards points engine

Analytics & operations dashboard (revenue, orders, riders, restaurants)

Support / helpdesk ticketing system

Scheduled delivery / pre-order system

Fraud detection & fake order prevention

Rider assignment algorithm (nearest-available + fallback logic)

1.3  Systems That Must Be MODIFIED (Not Rebuilt)

| Existing System | Required Modification | Effort |
| --- | --- | --- |
| Regions / Currencies | Change from GB/EUR to Indian cities + INR | 2 hrs |
| Tax Regions | Reconfigure for Indian GST (5%/12%/18% slabs) | 4 hrs |
| Customer Profile | Add: phone, food preferences, saved addresses[], default address | 8 hrs |
| Checkout Flow | Replace shipping selector with delivery address + slot picker | 16 hrs |
| Shipping Options | Replace with dynamic delivery fee calculation per restaurant | 12 hrs |
| Staff Portal RBAC | Add: restaurant_manager, rider_admin, support_agent roles | 8 hrs |
| Order Lifecycle | Extend statuses: confirmed → preparing → picked_up → delivered | 12 hrs |
| GoLocal Discounts Module | Add restaurant_id scoping + referral code support | 10 hrs |
| Product Catalog | Add restaurant_id FK, food-specific fields (prep time, dietary tags, spice level) | 14 hrs |
| Medusa Config | Update CORS, add Redis URL, add new module registrations | 2 hrs |
| Seed Data | Reseed with Indian cities, INR pricing, GST tax rates | 4 hrs |
| Staff Portal Orders Page | Build full order management UI (currently missing) | 24 hrs |

1.4  Systems That Should NOT Be Rebuilt

The following are battle-tested Medusa internals. Replacing them would be a massive waste of time and would introduce regressions:

Medusa core product/order/customer/inventory management (100+ managed tables)

MikroORM migration system — extend it, don't replace it

Medusa Admin UI (/app) — extend with widgets, don't rewrite

Custom discount module — extend with restaurant scoping

Staff portal auth (httpOnly cookie + proxy pattern) — it's solid

Next.js cache tag system — extend with new tags

Coolify + Docker deployment pipeline — reuse entirely

Turbo monorepo workspace — just add new apps (mobile/rider)

SECTION 2 — FOOD DELIVERY FEATURE ROADMAP

F-01  Location & Address System

Complexity: HIGH

Estimated Hours: 50–65 hrs

Dependencies: Google Maps Platform API keys, Google Places API, Geocoding API

The single most critical feature. Without accurate location, delivery radius, and distance calculation, nothing else in the platform works correctly. Every restaurant's serviceability, every delivery fee, and every ETA depends on this layer.

| Subtask | Hours | Notes |
| --- | --- | --- |
| Google Maps API integration (Places, Geocoding, Directions, Distance Matrix) | 8 hrs | API key management, quota limits |
| Address autocomplete on customer app (Places Autocomplete API) | 6 hrs | Debounced search, India-only filter |
| Reverse geocoding for GPS coordinates → readable address | 4 hrs | Used in rider location tracking |
| Saved addresses (home/work/other) per customer | 8 hrs | Medusa customer metadata extension |
| Default address selection + quick-switch UI | 4 hrs | Session persistence |
| Delivery zone / serviceability check per restaurant | 10 hrs | Polygon or radius-based check |
| Estimated delivery time calculation (Google Directions API) | 6 hrs | Real traffic data integration |
| Address validation on checkout | 4 hrs | Prevent invalid delivery addresses |
| Map view for restaurant picker (optional for MVP) | 9 hrs | Can be deferred |

RISK: Google Maps API billing can spike unexpectedly. Set hard budget caps in Google Cloud Console from day one. Cache Geocoding results aggressively (results rarely change).

F-02  Multi-Vendor Restaurant Management

Complexity: VERY HIGH

Estimated Hours: 90–110 hrs

Dependencies: F-01 (Location), Medusa product catalog extension

The core business entity. Each restaurant is a vendor with its own menu (Medusa products), categories, operating hours, delivery radius, cuisine tags, and rating. This requires a custom Medusa module extending the existing product catalog.

| Subtask | Hours | Notes |
| --- | --- | --- |
| Restaurant model (custom Medusa module: golocal-restaurants) | 10 hrs | name, logo, banner, cuisine_tags, lat, lng, radius_km, rating, is_open, fssai_number, gstin |
| Restaurant CRUD in staff portal | 12 hrs | Extend staff portal with restaurants section |
| Operating hours model (days × open/close time) | 6 hrs | Handle midnight cutover |
| Auto open/close status based on current time | 4 hrs | Cron job + real-time toggle |
| Restaurant-scoped menu (link restaurant_id to products) | 8 hrs | Add restaurant_id FK to product metadata |
| Menu categories per restaurant (reuse Medusa categories) | 4 hrs | Scoped category tree |
| Food item attributes (prep time, dietary tags: veg/non-veg/vegan, spice level, allergens) | 8 hrs | Product metadata extension |
| Restaurant search & filter (cuisine, rating, distance, open now) | 10 hrs | Algolia OR Medusa search extension |
| Restaurant listing page with distance sort | 8 hrs | GPS-based distance calculation |
| Restaurant detail page with menu + cart | 10 hrs | Full menu browsing experience |
| Restaurant banner images + gallery | 6 hrs | Cloudinary integration |
| Restaurant owner portal (limited staff permissions) | 10 hrs | Subset of staff portal for restaurant owners |
| Cuisine-based filtering + featured restaurants | 4 hrs | Platform-level curation |

F-03  Delivery Fee Calculation Engine

Complexity: MEDIUM

Estimated Hours: 30–40 hrs

Dependencies: F-01 (Location), F-02 (Restaurant), Google Distance Matrix API

| Subtask | Hours | Notes |
| --- | --- | --- |
| Base delivery fee per restaurant configuration | 4 hrs | Configurable per restaurant |
| Per-km rate calculation using Google Distance Matrix | 6 hrs | Cache distance results per customer-restaurant pair |
| Free delivery threshold (minimum order value) | 4 hrs | e.g., free delivery above ₹299 |
| Surge pricing multiplier (peak hours / bad weather) | 8 hrs | Time-based multiplier config |
| Small order fee (below minimum order value) | 3 hrs | Additional fee for small baskets |
| Rain / special event fee multiplier | 5 hrs | Manual admin toggle + scheduled rules |
| Delivery fee breakdown display in cart & checkout | 6 hrs | Transparent fee breakdown UI |
| Platform fee (GoLocal commission per order) | 4 hrs | Separate line item in order total |

F-04  Real-Time Order Tracking

Complexity: VERY HIGH

Estimated Hours: 80–100 hrs

Dependencies: Redis (pub/sub), Socket.io, F-05 (Rider System), F-07 (Push Notifications)

The most technically complex feature. Requires a persistent WebSocket layer, Redis pub/sub for event broadcasting, GPS location updates from the rider app, and a real-time map view for customers. This is the feature users open the app just to watch.

| Subtask | Hours | Notes |
| --- | --- | --- |
| Socket.io server setup on Medusa backend | 8 hrs | Namespaces: /customer, /rider, /restaurant |
| Redis pub/sub integration for order events | 6 hrs | Decouple event producers from consumers |
| Order status state machine (7 states) | 8 hrs | placed → confirmed → preparing → ready → picked_up → on_the_way → delivered |
| Restaurant receives order notification in real-time | 6 hrs | New order popup with accept/reject |
| Restaurant confirms order (with prep time estimate) | 4 hrs | KOT (Kitchen Order Ticket) style |
| Customer order status screen with live updates | 10 hrs | Auto-refreshing status cards + progress bar |
| Rider GPS location broadcast (every 5s from rider app) | 8 hrs | Compressed location stream via Redis |
| Customer map view showing rider location | 12 hrs | Google Maps with live pin movement |
| ETA recalculation as rider moves | 6 hrs | Directions API recalculation |
| Order completion confirmation screen | 4 hrs | Rating prompt trigger |
| Fallback to polling if WebSocket drops | 6 hrs | Graceful degradation |
| Admin real-time ops dashboard (all active orders) | 12 hrs | Live heatmap of orders + riders |

RISK: WebSocket connections at scale are resource-intensive. At 10,000 concurrent users, Socket.io requires careful horizontal scaling with sticky sessions or Redis adapter. Plan for this from day one.

F-05  Rider / Delivery Partner System

Complexity: VERY HIGH

Estimated Hours: 100–120 hrs

Dependencies: F-01 (Location), F-04 (Real-time), F-08 (Payments/Payouts)

| Subtask | Hours | Notes |
| --- | --- | --- |
| Rider data model (custom Medusa module: golocal-riders) | 8 hrs | name, phone, aadhaar, PAN, vehicle_type, vehicle_number, bank_account, status, current_lat/lng, is_available, rating |
| Rider onboarding flow (KYC document upload) | 12 hrs | Aadhaar + driving licence + bank account |
| Rider approval workflow in staff portal | 8 hrs | Admin reviews + approves riders |
| Rider availability toggle (online/offline) | 4 hrs | Simple toggle in rider app header |
| Auto-assign nearest available rider to order | 12 hrs | Haversine distance algorithm + queue |
| Rider push notification for new order assignment | 4 hrs | FCM with 60s accept timeout |
| Rider accepts / rejects order with reason | 6 hrs | Fallback to next nearest rider on reject |
| Rider picks up order (scan QR at restaurant) | 4 hrs | Optional QR code verification |
| Rider marks order delivered (photo proof optional) | 4 hrs | Customer signature or photo |
| Rider earnings per delivery (configurable per km/order) | 8 hrs | Transparent earning breakdown |
| Daily/weekly payout to bank account (Razorpay Payout API) | 12 hrs | Automated settlement |
| Rider performance metrics (on-time %, rating, acceptance rate) | 8 hrs | Staff portal analytics view |
| Rider chat with customer (optional) | 6 hrs | Can use third-party chat SDK |
| Rider penalty / deactivation workflow | 4 hrs | Admin action with reason logging |

F-06  Push Notifications (Firebase FCM + APNs)

Complexity: MEDIUM

Estimated Hours: 35–45 hrs

Dependencies: Firebase project, Apple Developer account (for APNs), F-04

| Notification Type | Recipients | Trigger | Priority |
| --- | --- | --- | --- |
| Order placed confirmation | Customer | Order created event | High |
| Order confirmed by restaurant | Customer | Restaurant confirms | High |
| Food being prepared | Customer | Prep start event | Normal |
| Rider assigned to your order | Customer | Rider assignment | High |
| Rider arrived at restaurant | Customer | Location checkpoint | Normal |
| Order picked up — on the way! | Customer | Rider pickup confirmed | High |
| Order delivered | Customer | Delivery confirmation | High |
| New order received | Restaurant app | Order placed | Critical |
| Order cancellation | Customer + Restaurant + Rider | Cancel event | High |
| New order assignment | Rider | Assignment event | Critical |
| Promo / offer notification | Customers (batch) | Marketing trigger | Low |
| Wallet cashback credited | Customer | Cashback event | Normal |

Implementation: Firebase Admin SDK in Medusa backend → Subscribe to order events via Medusa event system → Publish FCM notifications. Store device tokens in customer/rider metadata.

F-07  Indian Payment Integration (Razorpay)

Complexity: HIGH

Estimated Hours: 50–65 hrs

Dependencies: Razorpay merchant account (needs GST + business registration), Medusa payment provider

| Payment Method | Implementation | Hours | Fee |
| --- | --- | --- | --- |
| UPI (GPay, PhonePe, BHIM) | Razorpay UPI intent / QR | 8 hrs | ~1.8% |
| Debit / Credit Cards | Razorpay card checkout | 6 hrs | ~2% |
| Net Banking | Razorpay net banking | 4 hrs | ~1.8% |
| Wallets (Paytm, Amazon Pay) | Razorpay wallet integration | 4 hrs | ~1.8% |
| Cash on Delivery (COD) | Custom COD order flow (no gateway) | 10 hrs | 0% gateway, but COD fraud risk |
| In-App Wallet | Custom wallet balance (recharge via Razorpay) | 16 hrs | Recharge fee only |
| Razorpay Payout (rider earnings) | Razorpay Payout API | 12 hrs | ₹1-3 per payout |
| Refunds (auto + manual) | Razorpay Refund API + custom flow | 10 hrs | Free (gateway refunds) |
| Payment webhooks + verification | HMAC signature verification | 5 hrs | CRITICAL — verify all webhooks |

CRITICAL: Create a custom Medusa payment provider for Razorpay. Do NOT use the Stripe provider. Razorpay requires a registered Indian business with GST number.

F-08  OTP Phone Authentication

Complexity: MEDIUM

Estimated Hours: 25–35 hrs

Dependencies: MSG91 or Twilio account, Medusa auth extension

Phone number entry → OTP send via MSG91/Twilio

OTP verification → JWT token issuance

Account creation on first-time login (phone-first)

Link email optionally after phone auth

Biometric auth for subsequent logins (React Native Biometrics)

Token refresh flow (silent background refresh)

Admin OTP bypass for staff/restaurant portal (email+password stays)

F-09  GST / Tax System for India

Complexity: MEDIUM-HIGH

Estimated Hours: 25–35 hrs

| Tax Component | Rate | Applies To | Notes |
| --- | --- | --- | --- |
| Restaurant food (standalone, no AC) | 5% GST | Food items from non-AC restaurants | CGST 2.5% + SGST 2.5% |
| Restaurant food (AC restaurant) | 18% GST | Food from AC restaurants | No input tax credit for restaurants |
| Platform fee / delivery charge | 18% GST | GoLocal's service fee | GoLocal registered as online aggregator |
| FSSAI-required labeling | N/A | All food items | License number must appear on invoice |
| TDS on rider payouts (Section 194C) | 1% / 2% | Rider earnings above ₹30,000/yr | Platform must deduct TDS |
| GST on restaurant commission | 18% GST | GoLocal's commission from restaurant | Reverse charge applies |

IMPORTANT: Consult a CA (Chartered Accountant) specializing in Indian food aggregator platforms before going live. Tax rules for aggregators like Swiggy/Zomato are specific and evolving.

F-10  Ratings & Reviews System

Complexity: MEDIUM

Estimated Hours: 30–40 hrs

Order-verified reviews only (prevents fake reviews — trigger review prompt only after delivery)

Restaurant rating (1–5 stars) + written review

Food item-level rating (optional, shows on menu)

Rider rating (shown to rider, affects priority queue)

Restaurant can respond to reviews publicly

Review moderation in staff portal (flag / delete inappropriate reviews)

Automatic restaurant rating recalculation (rolling average, last 90 days weighted)

F-11  Offers, Coupons & Referrals

Complexity: LOW-MEDIUM (reuse existing)

Estimated Hours: 20–30 hrs

Dependencies: Existing GoLocal Discounts Module — EXTEND, do not rebuild

| Feature | Approach | Hours |
| --- | --- | --- |
| Restaurant-specific coupons (e.g., 20% off Domino's) | Add restaurant_id to golocal_discount model | 6 hrs |
| Platform-wide first-order discount | Extend existing global scope discount | 3 hrs |
| Referral code system (refer-a-friend ₹50 off) | New referral_codes table + attribution tracking | 12 hrs |
| Cashback offers (credited to wallet) | Post-delivery wallet credit via subscriber | 8 hrs |
| BOGO (Buy 1 Get 1) offers | New discount type in existing module | 6 hrs |
| Bundle deals (combo meals) | Product bundle pricing via Medusa price lists | 5 hrs |

F-12  Scheduled / Pre-Order Delivery

Complexity: MEDIUM

Estimated Hours: 20–28 hrs

Dependencies: @medusajs/draft-order (already installed), Medusa scheduled jobs

Time slot selection at checkout (30-min delivery windows)

Pre-order up to 2 days in advance

Draft order created immediately, activated at schedule time via Medusa job

Restaurant receives order notification at activation time (not booking time)

Customer can modify/cancel up to 30 mins before scheduled time

Reminder notification 1 hr before scheduled delivery

F-13  Cancellation & Refund Workflows

Complexity: MEDIUM-HIGH

Estimated Hours: 30–40 hrs

| Cancellation Scenario | Refund Policy | Processing Time | Notes |
| --- | --- | --- | --- |
| Customer cancels before restaurant confirms | 100% refund to original method | Instant | Auto-approve |
| Customer cancels after restaurant confirms | 50% refund (restaurant comp) | 2-3 business days | Requires manual review |
| Customer cancels after rider assigned | No refund (restaurant + rider comp) | N/A | Only for extreme cases |
| Restaurant cancels (out of stock etc) | 100% refund + platform credit ₹50 | Instant wallet credit | Restaurant penalty applies |
| Rider cannot find customer | 100% refund if no delivery attempt made | 24 hrs | Requires photo evidence |
| Wrong order delivered | 100% refund + replacement offered | 24-48 hrs | Photo proof required |
| Missing items in order | Partial refund for missing items | 24 hrs | Auto-credit to wallet |

F-14  In-App Wallet System

Complexity: MEDIUM-HIGH

Estimated Hours: 35–45 hrs

Wallet balance stored in customer metadata (or dedicated wallets table)

Wallet recharge via Razorpay (UPI / card / net banking)

Wallet balance at checkout — partial payment (wallet + card combo)

Cashback auto-credit via Medusa subscriber on order.completed event

Wallet transaction history (credit/debit ledger)

Wallet transfer / gifting between accounts (optional v2 feature)

Expired cashback handling (30-day validity on promotional cashback)

F-15  Loyalty / Rewards Points Engine

Complexity: MEDIUM

Estimated Hours: 35–45 hrs

| Feature | Detail | Hours |
| --- | --- | --- |
| Points earned per order (1 point = ₹1 spent) | Configurable earn rate per restaurant category | 8 hrs |
| Three-tier loyalty (Bronze / Silver / Gold) | Based on total orders or total spend in 90 days | 10 hrs |
| Tier benefits (extra % cashback, free delivery for Gold) | Applied at checkout automatically | 8 hrs |
| Points redemption at checkout | Minimum 50 points, up to 20% of order value | 8 hrs |
| Points expiry (12 months from last activity) | Scheduled job + reminder notification | 6 hrs |
| Loyalty leaderboard (top customers per city) | Optional gamification feature | 5 hrs |

F-16  Analytics & Operations Dashboard

Complexity: HIGH

Estimated Hours: 50–70 hrs

| Dashboard Module | Key Metrics | Hours |
| --- | --- | --- |
| Revenue Analytics | GMV, Net revenue, Commission earned, AOV (Average Order Value) by city/restaurant/time | 12 hrs |
| Order Analytics | Orders per hour, Cancellation rate, Avg prep time, Avg delivery time, Peak hours heatmap | 12 hrs |
| Restaurant Performance | Orders per restaurant, Rating trends, Menu item popularity, Out-of-stock frequency | 10 hrs |
| Rider Performance | Delivery time, On-time %, Acceptance rate, Earnings, Active hours per day | 10 hrs |
| Customer Analytics | New vs returning, LTV, Cohort retention, Churn indicators | 10 hrs |
| Ops Live View | Real-time orders map, Active riders on map, Unassigned orders alert | 12 hrs |
| Finance Reports | GST reports, TDS reports, Payout summaries, Settlement reports | 8 hrs |
| Fraud Reports | Cancelled orders pattern, COD abuse, Account anomalies | 6 hrs |

F-17  Support / Helpdesk System

Complexity: MEDIUM-HIGH

Estimated Hours: 40–55 hrs

Issue categories: Wrong order / Missing items / Late delivery / Payment issues / Rider behavior

In-app issue reporting (with order ID auto-attached)

Ticket creation → auto-assigned to support agent

Staff portal support queue with SLA timers

Customer compensation workflow (wallet credit / replacement)

Restaurant-facing support (commission disputes, menu issues)

Rider support (payout disputes, account issues)

Automated resolution for common issues (missing items → instant wallet credit)

Escalation workflow for unresolved tickets

Support analytics (resolution time, ticket volume, CSAT scores)

F-18  Inventory Synchronization

Complexity: MEDIUM

Estimated Hours: 20–30 hrs

Real-time item availability toggle (restaurant marks items as available/unavailable)

Auto-disable items based on stock count (Medusa inventory module)

Customer sees 'Currently Unavailable' badge on sold-out items

Restaurant receives low-stock alert for configurable threshold

Bulk menu availability toggle (e.g., mark all non-veg items unavailable)

Inventory reset at start of each operating day (configurable per restaurant)

SECTION 3 — MOBILE APP ARCHITECTURE

3.1  How Many Apps Are Required

| App | Users | Platform | Purpose | Priority |
| --- | --- | --- | --- | --- |
| Customer Food Delivery App | End consumers | iOS + Android | Browse restaurants, order food, track delivery, manage account, wallet | MVP — Critical |
| Rider / Delivery Partner App | Delivery riders | Android (primary), iOS (secondary) | Accept orders, navigate, mark delivery, view earnings | MVP — Critical |
| Restaurant Partner App | Restaurant owners/managers | Android (primary), Web (secondary) | Receive orders, manage menu, toggle availability, view reports | Phase 2 |
| Admin / Operations App | GoLocal ops team | Web (staff portal extension) | Monitor live orders, manage riders, handle support, view analytics | Phase 1 — Web only |

3.2  Technology Recommendation

RECOMMENDATION: React Native with Expo (EAS Build). Reasoning:

EXISTING CODEBASE IS TypeScript + React — team already knows the language

Expo EAS Build handles Play Store + App Store submissions without needing Mac for Android

Code sharing: ~60-70% logic shared between customer and rider app (auth, API client, location, notifications)

React Native + Expo has the largest food delivery app reference implementations

Faster iteration: OTA (over-the-air) updates via Expo Updates for JS-only changes without store re-submission

AVOID Flutter: Different language (Dart), steeper learning curve for a TypeScript team

3.3  Monorepo App Structure

Add to existing Turbo monorepo workspace:

| New App | Path | Tech | Shares With |
| --- | --- | --- | --- |
| Customer Mobile App | apps/mobile-customer/ | React Native + Expo SDK 52 | API client lib, auth logic, types |
| Rider Mobile App | apps/mobile-rider/ | React Native + Expo SDK 52 | API client lib, auth logic, location lib |
| Shared Mobile Lib | packages/mobile-shared/ | TypeScript | Both mobile apps |
| API Client SDK | packages/api-client/ | TypeScript (fetch + axios) | Backend + both mobile apps |

3.4  Customer App — High-Level Architecture

| Screen / Module | Key Features |
| --- | --- |
| Onboarding | Phone OTP login, location permission request, delivery address set |
| Home Feed | Nearby restaurants, promotional banners, cuisine filter chips, search bar |
| Restaurant Detail | Menu with categories, item customization (add-ons), restaurant info, reviews |
| Cart & Checkout | Cart summary, address selector, delivery slot, payment method, order summary |
| Order Tracking | Live status timeline, rider location on map, ETA countdown, rider contact |
| Order History | Past orders with reorder button, invoice download, review prompt |
| Profile & Wallet | Saved addresses, wallet balance, transaction history, loyalty tier |
| Notifications | FCM push + in-app notification center |
| Offers | Coupon list, referral code share, loyalty rewards |

3.5  Rider App — High-Level Architecture

HIGH-LEVEL ONLY — Full breakdown deferred to separate rider app planning document.

| Screen / Module | Key Features |
| --- | --- |
| Login / KYC | Phone OTP + document upload |
| Home / Status | Online/Offline toggle, current order, earnings today |
| Order Acceptance | Incoming order popup with 60s timer, restaurant location, customer location, accept/reject |
| Navigation | Google Maps navigation to restaurant, then to customer |
| Delivery Flow | Arrive at restaurant → pickup confirmation → navigate to customer → deliver → photo proof |
| Earnings | Per-delivery earnings, daily total, weekly payout schedule |
| Support | Report issue, contact GoLocal support |

3.6  Realtime Architecture

| Component | Technology | Role |
| --- | --- | --- |
| WebSocket Server | Socket.io + Redis Adapter | Bi-directional real-time events |
| Event Bus | Redis Pub/Sub + Medusa event system | Order status change broadcasting |
| Rider Location Stream | Socket.io → Redis → Customer app | GPS updates every 5 seconds |
| Order State Machine | Medusa workflow + custom subscriber | State transitions + notifications |
| Push Notification Queue | Firebase Admin SDK + Medusa job | Async notification delivery |
| Fallback Polling | REST API polling every 10s | When WebSocket is disconnected |

SECTION 4 — API + THIRD PARTY SERVICES

| Service | Why Needed | Free Tier | Est. Monthly Cost (₹) | Scaling Concern | Cheaper Alternative |
| --- | --- | --- | --- | --- | --- |
| Google Maps Platform (Places API) | Restaurant search autocomplete, address search, user location | $200 credit/month | ₹2,000–8,000 (post free tier) | API calls spike with every address search — cache results! | Here Maps API (cheaper per request) |
| Google Geocoding API | Convert lat/lng to address and vice versa | Included in $200 | ₹500–3,000 | Cache all geocoding results in Redis for 30 days | OpenStreetMap Nominatim (free but slower) |
| Google Directions API | ETA calculation for delivery | Included in $200 | ₹1,000–5,000 | Cache restaurant→customer routes (same routes repeat) | OSRM (self-hosted, free) |
| Google Distance Matrix | Delivery fee calculation (distance) | Included in $200 | ₹1,500–6,000 | Batch requests per order, cache aggressively | PostGIS distance calculation (free) |
| Firebase Cloud Messaging | Push notifications (Android + iOS) | FREE — unlimited | ₹0 | Very high scale still free | OneSignal (has free tier too) |
| Firebase Crashlytics | Mobile app crash reporting | FREE | ₹0 | Always free | Sentry (see below) |
| MSG91 (SMS OTP) | Phone number OTP verification | ₹0 (pay per SMS) | ₹1,500–8,000 (₹0.20–0.35 per OTP) | OTP volume = active users ÷ 30 days | Twilio (costlier), Fast2SMS (cheaper ₹0.15/SMS) |
| Razorpay (Payments) | UPI, cards, net banking, COD, payout to riders | No monthly fee | 2% per transaction (₹10,000 on ₹5L GMV) | Fee % stays flat — no hidden cost | PayU, Cashfree (similar fees) |
| Razorpay Payouts | Rider earnings bank transfer | ₹1–5 per transfer | ₹2,000–10,000 (depends on rider count) | High rider count = significant payout cost | PhonePe for Business payouts |
| Resend (Email) | Order confirmations, invoices, OTP backup | 3,000 emails/month free | ₹0–2,000 | Email volume very low vs order count | SendGrid, AWS SES (cheapest) |
| Sentry (Error Tracking) | Backend + mobile app error monitoring | 5,000 errors/month free | ₹0–3,500 (Team plan) | Essential for production — don't skip | GlitchTip (self-hosted free) |
| PostHog (Analytics) | User behavior, funnel analysis, feature flags | 1M events/month free | ₹0–8,000 | Free tier covers early stage well | Mixpanel, Amplitude (costlier) |
| Cloudflare (CDN + WAF) | CDN for images/static, DDoS protection, firewall | Free plan covers basics | ₹0–3,500 | WAF rules critical at scale | AWS CloudFront (usage-based) |
| Cloudinary (Image Hosting) | Restaurant images, food photos, rider photos optimized | 25 credits/month free (~25,000 transforms) | ₹0–4,000 | Food delivery is image-heavy — optimize aggressively | Bunny.net + self-hosted resize |
| Redis Cloud / Upstash | Caching, pub/sub, session storage, WebSocket adapter | Free 30MB / 10,000 req/day | ₹1,500–6,000 | WebSocket adapter needs low-latency Redis | Self-hosted Redis on VPS (cheapest) |
| Socket.io (Self-hosted) | WebSocket real-time layer | Free (open source) | Server cost only | Needs Redis adapter for multi-instance | Ably (managed, costlier) |

TOTAL ESTIMATED MONTHLY THIRD-PARTY COSTS at ~1,000 orders/day: ₹15,000 – ₹55,000/month. At 10,000 orders/day: ₹80,000 – ₹2,50,000/month.

SECTION 5 — SERVER + INFRASTRUCTURE ESTIMATION

5.1  Scale Definitions

| Scale | Daily Orders | Concurrent Users | Active Cities | Restaurants |
| --- | --- | --- | --- | --- |
| LOW (MVP / Pilot) | 50–500 | 50–500 | 1–2 | 10–50 |
| MEDIUM (Growth) | 500–5,000 | 500–5,000 | 3–10 | 50–500 |
| HIGH (Scale) | 5,000–50,000 | 5,000–50,000 | 10–30 | 500–5,000 |

5.2  Infrastructure Stack Per Scale

| Component | LOW Scale | MEDIUM Scale | HIGH Scale |
| --- | --- | --- | --- |
| Medusa Backend | 1× VPS (4 vCPU, 8GB) — Hetzner CX31 | 2× VPS (8 vCPU, 16GB) + Load Balancer | 4–8× VPS behind Hetzner LB + autoscale |
| Next.js Storefront | Same VPS or shared | 1× VPS (4 vCPU, 8GB) | Edge deployment (Vercel/Cloudflare Workers) |
| PostgreSQL | Managed Hetzner DB (1 vCPU, 2GB) | Managed DB (2 vCPU, 8GB) + read replica | Managed DB cluster (4 vCPU, 16GB) + 2 replicas |
| Redis | Redis on same VPS (256MB) | Redis Cloud Free → Starter ($7/month) | Redis Cloud Pro / Upstash ($50–200/month) |
| Socket.io Server | Same backend server | Dedicated 2× VPS (4 vCPU, 4GB) | Dedicated 4+ VPS with Redis adapter |
| File / Image Storage | Hetzner Object Storage (S3-compatible) | Cloudinary Free → Paid | Cloudinary + Cloudflare CDN |
| CDN | Cloudflare Free | Cloudflare Free + custom rules | Cloudflare Pro ($20/month) |
| Monitoring | UptimeRobot Free + Sentry Free | Sentry Team + Grafana + Prometheus | Full observability stack (Grafana Cloud) |
| Estimated Monthly Cost (INR) | ₹3,000 – ₹8,000/month | ₹15,000 – ₹40,000/month | ₹60,000 – ₹2,50,000/month |

5.3  Provider Comparison

| Provider | Best For | India Region? | Est. 8 vCPU/16GB/month | Verdict |
| --- | --- | --- | --- | --- |
| Hetzner Cloud (CURRENT) | Cost-efficiency, good EU/US performance | No (EU/US/SG only) | €24–38/month (~₹2,200–3,500) | BEST value — keep using for MVP + growth |
| Oracle Cloud Free Tier | Free always-free VMs (4 OCPU, 24GB ARM) | Yes (Mumbai, Hyderabad) | FREE (2× always-free ARM VMs) | Excellent for staging / non-critical services |
| AWS (Mumbai ap-south-1) | Full managed services, Indian latency | Yes (Mumbai) | $120–180/month (~₹10,000–15,000) | Expensive — use only when scaling requires it |
| DigitalOcean | Simple managed DBs, Spaces storage | No (SFO/NYC/SGP/FRA) | $96/month (~₹8,000) | Good middle-ground, lacks India region |
| Contabo VPS | Cheapest raw compute | No | $14/month (~₹1,200) | No managed services, manual everything |

RECOMMENDATION: Start on Hetzner (current setup). Add Oracle Cloud Free tier for staging. Consider Mumbai AWS only when latency becomes a customer complaint (likely at HIGH scale).

5.4  Docker + Deployment Architecture

| Service | Docker Strategy | Scaling Strategy |
| --- | --- | --- |
| Medusa Backend | Multi-stage Dockerfile (current) — keep | Horizontal: multiple instances behind LB. Use --workers flag for cluster mode |
| Next.js Storefront | Current Dockerfile — keep, add ISR | Edge deploy or multiple instances |
| Socket.io Realtime | New container: node:22-alpine + Socket.io | Must use Redis adapter for multi-instance sticky sessions |
| PostgreSQL | Managed service (NOT in Docker for production) | Managed DB handles backups, failover, replicas |
| Redis | Docker for dev, Redis Cloud for production | Redis Cluster for pub/sub at HIGH scale |
| Background Workers | Medusa jobs run in main process (low scale) or dedicated worker container | Separate worker container at MEDIUM+ scale |
| Mobile API Gateway | Nginx reverse proxy container (already Coolify-managed) | Rate limiting rules per endpoint |

SECTION 6 — PLAY STORE + APP STORE CHALLENGES

THIS IS THE MOST IMPORTANT SECTION. Most teams discover these blockers at the END of development. Reading this section now can save 2–4 months of wasted time.

6.1  Developer Account Setup & Costs

| Account | One-Time Cost | Annual Fee | Setup Time | Requirements |
| --- | --- | --- | --- | --- |
| Google Play Console | USD $25 (~₹2,100) — one-time forever | None | 1–3 days | Google account + payment method + identity verification |
| Apple Developer Program | USD $99/year (~₹8,300) — every year! | ₹8,300/year | 3–7 days | Valid Apple ID + credit card + D-U-N-S number (free but takes 5 business days to get) |
| Apple D-U-N-S Number | FREE via Dun & Bradstreet | N/A | 5–14 business days | CRITICAL: Get this FIRST before applying for Apple developer account. Requires registered company. |
| Apple Certificate (iOS Distribution) | Included in developer account | Renew yearly | 1–2 days | Requires Mac or Xcode (EAS Build handles this) |
| Android Keystore | Free (self-generated) | Never expires | 1 hour | CRITICAL: Store keystore file safely — if lost, you can NEVER update your app |

CRITICAL WARNING: Apple requires a registered legal business entity (not a sole proprietor trading name) for apps that process payments. Your GSTIN or company registration will be required.

6.2  Technical Build Requirements

| Requirement | Android | iOS | Expo/EAS Solution |
| --- | --- | --- | --- |
| Build environment | Can build on any OS | Requires macOS + Xcode | EAS Build — cloud builds on Mac servers |
| Minimum target SDK | SDK 26 (Android 8.0) minimum, SDK 33+ recommended | iOS 16+ recommended | Set in app.json/app.config.js |
| 64-bit requirement | Mandatory (already default in RN) | Mandatory | Default in React Native |
| App bundle format | .aab preferred (Play Store) — NOT .apk | .ipa file | eas build --platform android produces .aab |
| App signing | Upload keystore to Play Console for managed signing | Distribution certificate + provisioning profile | EAS handles credentials storage |
| Privacy manifest (iOS 17+) | N/A | REQUIRED — must declare all API usage (location, contacts, etc.) | expo-privacy-manifest plugin |
| Data safety form (Android) | Must fill in Play Console (privacy disclosures) | App Privacy section in App Store Connect | Prepare before submission — takes hours |
| Screenshot requirements | Phone + 7" tablet screenshots | 6.5" + 5.5" iPhone + iPad screenshots | Use Expo's screenshot tool or design in Figma |

6.3  Permission Handling — The Biggest Rejection Risk

| Permission | When Used | Play Store Risk | App Store Risk | Best Practice |
| --- | --- | --- | --- | --- |
| Location (Foreground) | Customer app: delivery address, restaurant finder | LOW — standard | LOW — standard | Request at point of use, not on app launch |
| Location (Background) | Rider app: continuous GPS tracking while delivering | HIGH — requires justification review | VERY HIGH — Apple scrutinizes this heavily. Must prove necessity. | Only request background location AFTER rider goes online. Show clear explanation screen. |
| Camera | Rider: delivery photo proof, Restaurant: menu photos | LOW | LOW | Request only when feature is triggered |
| Notifications | Order updates, promotions | LOW (Android auto-granted, can be ignored) | HIGH — iOS requires explicit permission. 60% of users deny if asked at wrong time. | Ask AFTER first successful order, not on app launch. Show a pre-prompt explaining value. |
| Contacts (if any) | Share referral code | MEDIUM — needs justification if accessed | MEDIUM | Don't access contacts at all — use Share API instead |
| Phone State (IMEI etc.) | Never needed — do NOT request | HIGH rejection risk | Will be rejected | Never request READ_PHONE_STATE unless telephony is core feature |
| Precise Location vs Approximate | Need Precise for delivery tracking | LOW — required for delivery apps | Must justify Precise vs Approximate location | Clearly explain why precise location is needed |

6.4  Payment Policy Issues — VERY HIGH RISK

This is the #1 silent app killer for food delivery apps. Read carefully:

| Policy Issue | Google Play | Apple App Store | Food Delivery Impact |
| --- | --- | --- | --- |
| In-app purchases (digital goods) | Must use Google Play Billing (30% fee) | Must use Apple In-App Purchase (30% fee) | FOOD = physical good. Food orders are EXEMPT from IAP rules. You NEVER pay 30% commission to Apple/Google on food orders. |
| In-app wallet recharge | GRAY AREA — if classified as 'stored value for digital goods', needs Google Pay Billing | GRAY AREA — Apple has rejected apps where wallet can be used for digital content. Food-only wallets are generally safe. | Keep wallet strictly for food orders. Never allow wallet to buy digital subscriptions or in-app content. |
| Subscription (loyalty/premium) | Google Play Billing required | Apple IAP required (30% fee) | If you charge a monthly 'GoLocal Prime' subscription, Apple takes 30%. Many apps use web signup flow to bypass (legal but tricky). |
| UPI / Razorpay in app | ALLOWED for physical goods | ALLOWED for physical goods (food) | Both platforms allow third-party payment for food/physical services. This is your main payment method. |
| COD (Cash on Delivery) | No restrictions | No restrictions | Safe — purely offline transaction |
| Rider earnings payout | Not visible to stores | Not visible to stores | Backend payout — completely irrelevant to store policy |

6.5  Legal Pages Required (Non-Negotiable)

Privacy Policy — Required by BOTH stores. Must be hosted at a permanent URL. Must disclose: location data usage, data retention, sharing with third parties (Google Maps, Razorpay, FCM), user rights to deletion.

Terms of Service / Terms of Use — Required. Must include: cancellation policy, refund policy, delivery terms, user conduct, restaurant partnership terms.

Refund & Cancellation Policy — Must be clearly stated BEFORE purchase (checkout screen). Required by Consumer Protection Act 2019 (India).

FSSAI Aggregator License — Required to operate a food delivery aggregator platform in India. Apply at fssai.gov.in. Takes 30–60 days to get.

Data Localisation Compliance — Sensitive personal data (payment data) must be processed in India per RBI guidelines when using Razorpay.

Cookie Policy — Required by Google Play and App Store if using analytics.

Grievance Officer details — Required under Information Technology (Intermediary Guidelines) Rules 2021 for Indian apps. Must be a named person with contact info.

6.6  App Review Rejection Risks — Food Delivery Specific

| Rejection Trigger | Store | How to Avoid |
| --- | --- | --- |
| App crashes on first launch | Both | Thorough testing on multiple physical devices before submission. Expo prebuild for testing on device. |
| Background location without clear justification (rider app) | Apple (very strict) | Add NSLocationAlwaysAndWhenInUseUsageDescription + show in-app explanation screen before requesting |
| Missing privacy policy URL in app metadata | Both | Add before first submission — not after rejection |
| Payment flow looks like it's for digital goods | Apple IAP team | Make it clear food is physical. Show restaurant photos, delivery address, etc. |
| App contains LIVE but placeholder/demo content | Both | Submit only when real restaurants are live. Avoid test data visible to reviewers. |
| Copyrighted food images or restaurant logos | Both (especially if reported) | Use only owned images or properly licensed stock photos |
| Delivery radius or serviceability check not working in reviewer's location (San Jose / Cupertino) | Both | Add a test mode or demo restaurant available in all locations for reviewer testing. OR note in review notes. |
| Missing account deletion option (iOS 17+) | Apple (mandatory) | Add 'Delete Account' in profile settings. This is now mandatory. |
| In-app subscription without IAP (if any subscription exists) | Apple | Use web-only signup for any subscription tiers |
| Misleading app description / screenshots | Both | Match screenshots to actual app UI exactly |

6.7  TestFlight Process (iOS)

TestFlight is Apple's beta testing platform — required step before App Store submission

Internal testing: up to 100 testers, no Apple review, available within minutes of upload

External testing: up to 10,000 testers, requires basic Apple review (usually 24-72 hours)

EAS Build produces .ipa file → submit to App Store Connect → enable TestFlight

TestFlight builds expire after 90 days — keep uploading new builds during development

IMPORTANT: Start TestFlight distribution at least 30 days before planned launch to gather feedback

Crashlytics / Sentry must be integrated BEFORE TestFlight to catch crashes from beta users

6.8  Android Play Store Timeline

| Phase | Timeline | Notes |
| --- | --- | --- |
| Developer account setup | 1–3 days | Pay $25, verify identity |
| First app submission review | 3–7 days | Google manually reviews first-time submissions more carefully |
| Subsequent updates | 2–4 hours | Automated review for updates to existing apps |
| Play Store Internal Testing | Immediate (no review) | Up to 100 testers — use for team testing |
| Play Store Open Testing | 24–48 hours | Public opt-in beta |
| Production release | Review + staged rollout: 1–2 days | Start with 10% rollout, watch crashes |

6.9  EAS (Expo Application Services) Strategy

Use EAS Build for all production builds — handles Android Keystore + iOS certificates in the cloud

Use EAS Submit to automate Play Store + App Store submission directly from CLI

Use EAS Update for OTA (over-the-air) JavaScript updates — deploy JS fixes WITHOUT store re-submission

Expo SDK 52 is current stable — DO NOT use SDK 51 or older for new projects

EAS Build pricing: Free tier gives 30 builds/month. EAS Production plan ($29/month) gives 500 builds/month

CRITICAL: The Android Keystore generated by EAS is stored in EAS servers. DOWNLOAD AND BACKUP your keystore immediately. Loss = cannot update app ever again.

iOS certificates managed by EAS — but ensure Apple Developer account is paid (renew yearly or builds stop)

SECTION 7 — BUSINESS + OPERATIONAL CHALLENGES

7.1  Delivery Operations

| Challenge | Impact | Mitigation |
| --- | --- | --- |
| Rider supply-demand mismatch at peak hours | HIGH — orders pile up, ETAs balloon, churn | Surge incentives for riders (₹50 bonus per peak-hour delivery), minimum guarantee pay per hour online |
| Last-mile navigation in India (poor addressing) | HIGH — riders can't find customers in dense urban areas | Mandatory landmark field in address, custom location pin on map, rider can call customer (masked number) |
| Bad weather (monsoon) delivery disruptions | MEDIUM — customer expectations vs. reality | Proactive ETA extension notification, weather surcharge toggle, allow cancellation without penalty |
| Rider motorcycle/scooter breakdowns | LOW frequency, HIGH impact on active order | Rider SOS button → ops team intervention, order reassignment within 5 mins |
| Delivery bag hygiene and tamper-proof sealing | MEDIUM — customer trust | Mandate tamper-evident stickers for restaurant packaging (policy, not technical) |

7.2  Rider Onboarding & Compliance

MANDATORY KYC: Aadhaar card (identity), Driving Licence (vehicle authorization), PAN card (for TDS), bank account (for payouts), vehicle RC (registration certificate)

Background check: Consider integrating AuthBridge or IDfy for automated KYC verification (cost: ₹30–100 per rider)

Rider agreement contract (mandatory before activation): delivery terms, conduct policy, TDS acknowledgment

Rider equipment: Delivery bag (provide or subsidize), smartphone with data plan (rider's own), helmet (legal requirement)

Legal classification: Riders are typically gig workers (not employees) — ensures platform isn't liable for ESI/PF. Consult labour lawyer for compliance with Code on Social Security 2020 (OSHC rules).

Rider app training: Mandatory onboarding tutorial before first order acceptance

7.3  Restaurant Onboarding

FSSAI license number mandatory (without this restaurant cannot be listed by law)

GSTIN mandatory for restaurants with turnover > ₹20 lakhs (must appear on invoice)

Commission agreement: Typical Indian market rates — 20–25% for exclusive, 15–20% for non-exclusive

Menu photography: Invest in consistent food photography. Ugly menu photos = low conversion. Budget ₹3,000–8,000 per restaurant for photo shoot.

Restaurant POS integration: Many restaurants use Petpooja, POSist, Posify — integration allows auto-sync of menu and availability

Exclusivity negotiations: Large chains (McDonald's, KFC) demand specific platform terms. Start with independent local restaurants.

Bank account verification: Verify restaurant's bank account before going live to prevent payment disputes

7.4  Fraud & Abuse Prevention

| Fraud Type | Risk Level | Detection Method | Prevention |
| --- | --- | --- | --- |
| COD order abandonment (customer not home) | HIGH in India | Rider marks 'customer unreachable' — flag repeat offenders | Limit COD to verified accounts with order history. Charge ₹25 COD fee to reduce fake orders. |
| Fake review bombing (competitor attacks restaurant) | MEDIUM | Detect sudden rating drops from new accounts | Verified purchase reviews only. Rate-limit reviews per account. |
| Referral code abuse (multiple accounts one person) | HIGH | Phone number deduplication + device fingerprinting | One referral bonus per unique phone number. Delay bonus until referred user places 2nd order. |
| Wallet fraud (stolen cards, fake UPI) | HIGH | Razorpay fraud detection + velocity checks | Limit wallet recharge to ₹2,000 for new accounts. Mandatory OTP for wallet > ₹500. |
| Restaurant collusion (fake orders for commission theft) | MEDIUM | Analyze orders from single phone → single restaurant | Flag and suspend restaurants with > 5% order cancellation rate from same customer pool. |
| Rider marking delivered without delivery | MEDIUM | OTP delivery confirmation (customer receives OTP, gives to rider) | OTP-based delivery confirmation for orders > ₹500. Photo proof for all COD orders. |
| Account takeover | MEDIUM | Unusual login location, device change | Re-OTP on suspicious login. Notify previous device on new device login. |

7.5  Commission & Revenue Model

| Revenue Stream | Typical Rate | Notes |
| --- | --- | --- |
| Restaurant commission on order value | 15–25% of food order value | Primary revenue. Negotiated per restaurant tier. |
| Delivery fee (customer pays) | ₹20–80 per order depending on distance | Covers ~40-60% of rider cost. Platform subsidizes rest. |
| Platform convenience fee | ₹3–10 per order | Small fixed fee — high margin |
| In-app advertising (restaurant promotion) | ₹5,000–50,000/month per slot | Restaurants pay for top-of-feed placement |
| GoLocal Prime subscription (optional) | ₹149/month | Free deliveries + exclusive offers. Subscription revenue. |
| Surge fee margin | Platform keeps 20–30% of surge fee | Customer pays extra, most goes to rider |
| Cloud kitchen revenue share | Higher commission (25–35%) | Platform-owned or platform-promoted cloud kitchens |

7.6  Serviceability Zones & City Expansion Strategy

Start in ONE zone of ONE city. Master delivery times, rider supply, and restaurant quality before expanding.

Target tier-2 cities first (Indore, Jaipur, Kochi, Coimbatore) — less competition from Swiggy/Zomato, lower CAC

Minimum viable restaurant density: 8–10 restaurants per 3km² delivery zone for acceptable customer choice

Minimum viable rider density: 1 rider per 0.5km² in peak zones during peak hours

Geofencing zones allow hard serviceability boundaries — customer gets 'We're not in your area yet' before entering checkout

Waitlist feature for unserviced areas drives organic pre-launch demand and informs city prioritization

SECTION 8 — FINAL MASTER TABLES

8.1  Major Modules + Effort Estimates

| Module | Phase | Est. Hours | Team | Complexity |
| --- | --- | --- | --- | --- |
| Gap fixes: INR, GST, customer profile, checkout | MVP | 60 hrs | 1 Backend + 1 Frontend | MEDIUM |
| F-01: Location & Address System | MVP | 55 hrs | 1 Backend + 1 Frontend | HIGH |
| F-02: Multi-Vendor Restaurant Management | MVP | 100 hrs | 2 Backend + 1 Frontend | VERY HIGH |
| F-03: Delivery Fee Engine | MVP | 35 hrs | 1 Backend + 1 Frontend | MEDIUM |
| F-04: Real-Time Order Tracking | MVP | 90 hrs | 2 Backend + 1 Frontend | VERY HIGH |
| F-05: Rider / Delivery Partner System | MVP | 110 hrs | 2 Backend + 1 Frontend | VERY HIGH |
| F-06: Push Notifications (FCM) | MVP | 40 hrs | 1 Backend + 1 Mobile | MEDIUM |
| F-07: Razorpay Payment Integration | MVP | 58 hrs | 1 Backend + 1 Frontend | HIGH |
| F-08: OTP Phone Auth | MVP | 30 hrs | 1 Backend + 1 Frontend | MEDIUM |
| F-09: GST Tax System | MVP | 30 hrs | 1 Backend | MEDIUM |
| F-10: Ratings & Reviews | Phase 2 | 35 hrs | 1 Backend + 1 Frontend | MEDIUM |
| F-11: Offers, Coupons & Referrals (extend existing) | MVP | 25 hrs | 1 Backend + 1 Frontend | LOW |
| F-12: Scheduled Delivery | Phase 2 | 24 hrs | 1 Backend + 1 Frontend | MEDIUM |
| F-13: Cancellation & Refund Workflows | MVP | 35 hrs | 1 Backend + 1 Frontend | MEDIUM-HIGH |
| F-14: In-App Wallet | Phase 2 | 40 hrs | 1 Backend + 1 Frontend | MEDIUM-HIGH |
| F-15: Loyalty / Rewards Points | Phase 3 | 40 hrs | 1 Backend + 1 Frontend | MEDIUM |
| F-16: Analytics Dashboard | Phase 2 | 60 hrs | 1 Backend + 1 Frontend | HIGH |
| F-17: Support / Helpdesk | Phase 2 | 48 hrs | 1 Backend + 1 Frontend | MEDIUM-HIGH |
| F-18: Inventory Sync | MVP | 25 hrs | 1 Backend + 1 Frontend | MEDIUM |
| React Native Customer App | MVP | 200 hrs | 2 Mobile devs | VERY HIGH |
| React Native Rider App | MVP | 120 hrs | 1 Mobile dev | HIGH |
| Restaurant Partner Web Portal | Phase 2 | 80 hrs | 1 Frontend | MEDIUM-HIGH |
| Legal pages + App Store preparation | MVP | 30 hrs | 1 dev + legal consult | MEDIUM |
| Infrastructure: Redis, WebSocket, Docker | MVP | 30 hrs | 1 DevOps | MEDIUM |
| TOTAL MVP ESTIMATE |  | ~970 hrs |  |  |

8.2  Monthly API / Service Cost Estimates

| Service | LOW Scale | MEDIUM Scale | HIGH Scale |
| --- | --- | --- | --- |
| Google Maps Platform | ₹2,000 | ₹12,000 | ₹60,000 |
| MSG91 (SMS OTP) | ₹1,500 | ₹6,000 | ₹30,000 |
| Razorpay payment processing | ₹5,000 (2% of ₹2.5L GMV) | ₹40,000 (2% of ₹20L GMV) | ₹3,00,000 (2% of ₹1.5Cr GMV) |
| Razorpay Payouts (riders) | ₹500 | ₹4,000 | ₹25,000 |
| Firebase (FCM) | ₹0 | ₹0 | ₹0 |
| Sentry (error tracking) | ₹0 (free) | ₹2,800 | ₹7,000 |
| PostHog (analytics) | ₹0 (free) | ₹0 (free) | ₹6,000 |
| Cloudinary (images) | ₹0 (free) | ₹3,000 | ₹12,000 |
| Redis Cloud | ₹1,000 | ₹3,500 | ₹15,000 |
| Resend (email) | ₹0 (free) | ₹1,500 | ₹5,000 |
| Cloudflare | ₹0 (free) | ₹0 (free) | ₹1,700 (Pro) |
| TOTAL THIRD-PARTY | ₹10,000/month | ₹72,800/month | ₹4,61,700/month |

8.3  Infrastructure Cost Estimates

| Component | LOW (₹/month) | MEDIUM (₹/month) | HIGH (₹/month) |
| --- | --- | --- | --- |
| Hetzner VPS (backend + WebSocket) | ₹3,000 (CX31) | ₹10,000 (2× CX41) | ₹30,000 (4× CX51 + LB) |
| Managed PostgreSQL | ₹1,500 (Hetzner DB) | ₹5,000 (Hetzner DB + replica) | ₹18,000 (cluster) |
| Redis | ₹0 (same VPS) | ₹3,500 (Redis Cloud Starter) | ₹15,000 (Redis Cloud Pro) |
| Hetzner Object Storage (S3) | ₹500 (1TB) | ₹1,500 | ₹6,000 |
| CDN (Cloudflare) | ₹0 (Free) | ₹0 (Free) | ₹1,700 (Pro) |
| Monitoring (UptimeRobot + Grafana) | ₹0 | ₹2,000 | ₹6,000 |
| TOTAL INFRA | ₹5,000/month | ₹22,000/month | ₹76,700/month |

8.4  App Architecture Summary

| App | Framework | Build Tool | Deployment | Timeline |
| --- | --- | --- | --- | --- |
| Customer App (iOS + Android) | React Native + Expo SDK 52 | EAS Build | Play Store + App Store | ~200 hrs dev + 2–4 weeks review |
| Rider App (Android primary) | React Native + Expo SDK 52 | EAS Build | Play Store (primary) + App Store | ~120 hrs dev + 1–2 weeks review |
| Web Storefront (existing) | Next.js 15 App Router | Docker + Coolify | VPS (Hetzner) | Extend existing |
| Staff + Ops Portal (existing + extend) | Next.js 15 (embedded) | Docker + Coolify | VPS (Hetzner) | Extend existing |
| Restaurant Partner Portal | Next.js 15 (new section) | Docker + Coolify | VPS (Hetzner) | Phase 2 |

8.5  High-Risk Areas

| Risk | Category | Severity | Mitigation |
| --- | --- | --- | --- |
| Apple App Store background location rejection (rider app) | App Store | CRITICAL | Pre-permission explanation screen + privacy manifest |
| Razorpay merchant account approval delay (2–4 weeks) | Payments | CRITICAL | Apply for Razorpay account IMMEDIATELY — don't wait for dev to finish |
| FSSAI aggregator license delay (30–60 days) | Legal/Compliance | CRITICAL | Apply for FSSAI ASAP — this blocks launch |
| Android Keystore loss = cannot update app ever | Android Build | CRITICAL | Backup to 3 locations on day one of EAS build setup |
| WebSocket scaling at peak hours (dinner rush) | Infrastructure | HIGH | Redis Socket.io adapter from day one |
| Google Maps cost overrun (no budget cap set) | API Cost | HIGH | Set hard billing alert + cap in Google Cloud from day one |
| COD fraud (fake orders, customer unreachable) | Business | HIGH | OTP delivery confirmation + COD history scoring |
| GST classification error (platform fee rate) | Tax/Legal | HIGH | Hire a CA with food aggregator experience |
| Rider supply shortage at launch | Operations | HIGH | Onboard 3× minimum required riders before launch |
| Play Store first submission rejection (7-day delay) | App Store | MEDIUM | Submit to internal testing early, fix all issues before production release |

8.6  MVP vs Advanced Features

| Feature | MVP? | Phase | Rationale |
| --- | --- | --- | --- |
| Location + address system | YES | 1 | Without this nothing works |
| Multi-vendor restaurant listing | YES | 1 | Core product |
| Cart + checkout with delivery fee | YES | 1 | Core product |
| Razorpay UPI + Cards + COD | YES | 1 | Revenue blocker |
| OTP phone auth | YES | 1 | India-first auth |
| Basic order tracking (status updates, no map) | YES | 1 | Map tracking can come in 1.1 |
| Push notifications (FCM) | YES | 1 | Core UX |
| Rider system + assignment | YES | 1 | Core operations |
| Cancellation + refund flows | YES | 1 | Consumer Protection Act requirement |
| GST on orders | YES | 1 | Legal requirement |
| Customer mobile app | YES | 1 | Primary interface |
| Rider mobile app | YES | 1 | Primary interface |
| Live rider map tracking | DEFER | 1.1 | Add in first post-launch update |
| Ratings & reviews | DEFER | 2 | Nice to have, not blocking |
| In-app wallet | DEFER | 2 | Can launch without |
| Scheduled delivery | DEFER | 2 | Low demand at early stage |
| Loyalty points | DEFER | 3 | Retention feature, not acquisition |
| Restaurant partner app | DEFER | 2 | Web portal sufficient at start |
| Helpdesk system | DEFER | 2 | Manual support at MVP stage |
| Advanced analytics | DEFER | 2 | Basic Medusa admin covers MVP |
| Social sharing / viral features | NO | 3 | Build audience first |
| AI-based recommendations | NO | 4 | Need enough data first |

SECTION 9 — EXECUTION STRATEGY

9.1  Recommended Development Order

| Sprint | Weeks | Focus | Deliverables |
| --- | --- | --- | --- |
| Sprint 0 | Week 1–2 | Foundation & Legal | 1. Apply for Razorpay merchant account 2. Apply for FSSAI aggregator license 3. Apply for Apple D-U-N-S number 4. Create Google Play Console + Apple Developer accounts 5. Set up Google Maps API keys + billing alerts 6. Set up Firebase project (FCM) 7. Set up MSG91 SMS account 8. Configure Redis on VPS 9. Reseed database for India (INR, GST, Indian cities) |
| Sprint 1 | Week 3–5 | Core Architecture | 1. Customer profile extension (phone, saved addresses) 2. OTP phone authentication (MSG91) 3. Google Maps + Places API integration 4. Delivery address system (saved addresses + autocomplete) 5. Restaurant module (golocal-restaurants custom module) |
| Sprint 2 | Week 6–9 | Restaurant + Menu System | 1. Restaurant CRUD in staff portal 2. Operating hours model + auto open/close 3. Menu management (restaurant-scoped products) 4. Food item attributes (dietary, prep time) 5. Delivery zone + serviceability check 6. Restaurant listing + detail pages (web storefront) |
| Sprint 3 | Week 10–12 | Orders + Payments | 1. Razorpay payment provider for Medusa 2. UPI + card + COD payment flows 3. Delivery fee calculation engine 4. GST calculation on orders 5. Order status extension (food delivery states) 6. Cancellation + refund workflows |
| Sprint 4 | Week 13–16 | Real-Time Layer | 1. Socket.io server + Redis adapter 2. Order event system (Medusa subscribers) 3. Restaurant real-time order notifications 4. Customer order status live updates 5. Rider system backend (golocal-riders module) 6. Rider assignment algorithm |
| Sprint 5 | Week 17–20 | Mobile Apps | 1. Expo project setup (customer + rider apps) 2. Customer app: auth, home feed, restaurant detail, cart 3. Customer app: checkout, order confirmation, order tracking 4. Rider app: auth, order acceptance, navigation flow, delivery confirmation 5. FCM push notifications integration in both apps |
| Sprint 6 | Week 21–23 | Polish + App Store Prep | 1. App Store / Play Store metadata (screenshots, descriptions) 2. Privacy policy + Terms of Service pages live 3. Account deletion feature (Apple mandatory) 4. Privacy manifest (iOS 17+) 5. Crashlytics + Sentry integration 6. TestFlight beta testing 7. Play Store internal testing 8. Performance testing + load testing |
| Sprint 7 | Week 24 | LAUNCH | 1. Play Store production release (staged 10% rollout) 2. App Store submission 3. Onboard 5–10 pilot restaurants 4. Onboard 20–30 pilot riders 5. Monitor crash rates, order success rates, payment success rates 6. War room for first 48 hours |

9.2  Fastest Path to Revenue

WEEK 1: Apply for Razorpay + FSSAI + Apple D-U-N-S immediately. These have lead times — no code accelerates them.

WEEK 2: Onboard 3–5 restaurants for pilot. Real restaurants on platform = real test data = real orders at launch.

WEEK 3: Build web ordering first (existing storefront modified). Generate first revenue before mobile apps are done.

WEEK 10: Launch web-based ordering (no mobile app needed). Capture orders from desktop/mobile browser.

WEEK 20: Release mobile apps. This multiplies conversion rate by 2–3× vs. web-only.

DAY 1 OF LAUNCH: 20% platform commission from day one. Never offer 0% commission — it sets wrong expectations.

9.3  Most Dangerous Technical Traps

| Trap | Why Dangerous | How to Avoid |
| --- | --- | --- |
| Building real-time without Redis from day one | Socket.io breaks at 2+ backend instances without Redis adapter | Set up Redis adapter in Sprint 4 before first real-time line of code |
| Google Maps unbounded API usage | One viral moment can generate ₹50,000 in Maps costs overnight | Set hard billing cap on day one. Cache all geocoding + routing results. |
| Storing Razorpay payment data on your own servers | PCI DSS violation, RBI non-compliance | Never store raw card data. Let Razorpay handle all PCI scope. |
| Building custom auth instead of extending Medusa | Custom auth bypasses Medusa's token system, breaking admin | Extend Medusa auth module with phone OTP provider |
| Rebuilding order management instead of extending Medusa | Medusa's order system handles inventory, fulfillment, returns — rebuilding costs 3× time | Add food delivery states as Medusa order metadata + extend status workflow |
| Releasing rider app without background location explanation | Apple rejects app — 2–4 week delay to resubmit | Add explanation screen and privacy manifest in Sprint 6 before ANY submission |
| Losing Android Keystore file | Cannot update Android app ever — must republish as new app with new package name | Back up keystore to 3 locations on day of creation |
| Launching with COD before fraud controls | Coordinated COD fraud can cost ₹50,000+ in first week in a new city | Launch with UPI-only. Add COD only after 500+ successful orders in a zone. |
| No load testing before launch | Dinner rush on day 1 at 6–9pm can take down server | Load test with k6 or Locust to 10× expected peak before launch |

9.4  What Must Be Handled from Day One (No Deferral)

SECURITY: HMAC verification on ALL Razorpay webhooks — payment fraud starts immediately

SECURITY: Rate limiting on OTP endpoint (prevent SMS bombing — ₹50,000 bill in one night)

LEGAL: Privacy Policy live before first user — Play Store + App Store require a URL

LEGAL: FSSAI aggregator license application — apply in Sprint 0 before development starts

OPERATIONS: Rider assignment timeout (60 seconds) — if no rider accepts, auto-escalate immediately

MONITORING: Sentry error tracking from Sprint 1 — blind production is unacceptable

BUSINESS: Razorpay account activated before Sprint 3 payments work — 2-week KYC delay

GOOGLE MAPS: Billing cap set in Google Cloud on day API keys are created

DATABASE: PostgreSQL backups configured in Hetzner before going to production

9.5  Monetization Timeline

| Month | Revenue Event | Est. Monthly Revenue |
| --- | --- | --- |
| Month 1–3 (Web launch) | First orders from pilot restaurants, 20% commission | ₹10,000 – ₹50,000 |
| Month 4–6 (App launch) | Mobile apps live, conversion increases 2–3× | ₹50,000 – ₹2,00,000 |
| Month 7–12 (Growth) | Multiple restaurants, rider network established, ads revenue starts | ₹2,00,000 – ₹10,00,000 |
| Year 2 (Scale) | Multiple cities, GoLocal Prime subscription, cloud kitchen revenue | ₹10,00,000 – ₹50,00,000+ |

9.6  Final Recommendation — MVP Definition

The minimum viable product that generates revenue and proves the concept in ONE zone of ONE city:

✅ 8–15 real restaurants onboarded (own zone, tested menu, operating hours set)

✅ 20–40 verified riders in the zone

✅ Razorpay UPI + Cards working (skip COD for month 1)

✅ Basic order tracking (status updates, NO live map — defer map to 1.1)

✅ Push notifications for order status changes

✅ Customer mobile app on Play Store (Android first — faster review)

✅ iOS app on TestFlight (while App Store review in progress)

✅ Web ordering interface for desktop orders

✅ FSSAI license in hand before first public user

✅ Privacy Policy + T&C live on domain

✅ Manual support via WhatsApp Business (no helpdesk system needed at MVP)

✅ Basic analytics in Medusa admin (order count, revenue — no custom dashboard needed)

❌ Wallet, loyalty, referrals, advanced analytics, restaurant app — ALL deferred

──────────────────────────────────────────────────────────────────────────────────────────

ESTIMATED TOTAL MVP EFFORT: 970 hours (3-4 developers, 5-6 months)

ESTIMATED TOTAL MVP COST (infra + APIs + legal): ₹30,000–60,000 one-time setup + ₹15,000–40,000/month running

ESTIMATED TOTAL TIME TO FIRST REVENUE: 3 months (web) | 5–6 months (apps)

BIGGEST NON-TECHNICAL BOTTLENECK: FSSAI license + Razorpay merchant approval. Start BOTH on Day 1 of Sprint 0.